## Alexandria Jaycees

## Chairman’s Planning Guide

| Chapter Name and Number: | Alexandria, #2 |
| --- | --- |
| State Name and Number: | Virginia, #45 |
| Project Name: | Mardi Gras parade |
| Project Chair and Contact Info: | See addendum |
| CPG Category and Supervisor: | Membership Activation and Individual Development Sharon S., Vice President |

PLANNING

1.  Primary Purpose (What Is The One Reason You Want To Successfully Run This Project?)

We want to offer an opportunity for Jaycees to socialize and enjoy the local take on Mardi Gras.

State very concisely what the one objective of the project is.  Any explanation of what the project is should be included in #2 below.  The purpose should relate somehow to ID’s “single project category:”  Member Development (Leadership Development or Life Improvement)

2.  Give a brief description of the proposed project and background information.  Follow this with a listing of the specific and measurable goals to be accomplished by this project.

Describe what will actually take place during the project (Example:   The chapter will sell doughnuts at $2 per dozen to raise money for the chapter treasury.)

Then, include the background information.  A suggested format might be:  In the Chapter Plan of the Year for 97-98, the need for ____ was identified.  If you need a copy of the needs assessment from the plan of the year, I can provide it to you.

Goals for the project should be specific and measurable to aid in later evaluation.  Specific and measurable can be guaranteed by answering the who, what, where, when questions (i.e., Have 35 members participate in the project, Raise $200, Hike five miles in four hours, etc.).

We will meet for a quick bite and a cocktail at Eleventh Street Lounge in Clarendon, and then walk up Clarendon Blvd around 7:45 to watch the best Mardi Gras parade in Northern Virginia.  We’ll catch beads, look festive, and have a great time.

| Goal #1 | To have 5 Alexandria Jaycees members attend |
| --- | --- |
| Goal #2 | To have 3 non-members attend |

3. What Are The Specific Manpower Assignments? (Show Names And Duties)

See addendum.

Update Director name and Chairperson name, and add to/delete from this list as necessary.  The purpose of this question is to ensure the chairperson has thoroughly considered all people who will play a role in this project, and what role they will play.

4.  What Specific Materials, Supplies And Resources Will Be Required?

Update and add to as necessary.  Completion of this section ensures that the chairperson has considered all “stuff” needed to propose, promote, run, and complete this project.

| What | Who | When Needed |
| --- | --- | --- |
| Location and Directions | Sharon S., Cathy L. | Jan 28 -- Announce at meeting |
|  |  | February 4 -- Put on list serv |
| Communications |  |  |
| CPG | Sharon S. Presentation: Sharon S. | Date January 21 |
| Flyers | Sharon S. | January 28 |
| Listeserve | Sharon S./Dan C. | Date: January 22, January 29, February 4 |
| Hotline | Tim C. | Mention if room |
| Personnel |  |  |
| Preliminary Interest Sign-Up Sheet | Cathy L. | January 28 |
| Project sign-in sheet | Sharon S. | February 5 |

5.  Describe The Potential Problems And Solutions To Successfully Complete This Project.

| Problem 1 : | Smaller turnout of Jaycee members than expected |
| --- | --- |
| Solution 1: | Continue to have fun with smaller group |
| Problem 2: | Difficulty in finding location |
| Solution 2: | Advertise location in advance on list serv. Ask people to call or text you if they get confused |
| Problem 3 | It’s a school night. People don’t want to go out. |
| Solution 3 | Allow people to leave after parade ends. Don’t plan official outing after parade, but plan it before. |

- Complete A Proposed Budget Indicating All Anticipated Income And Expenses.

| INCOME: | PROJECTED | ACTUAL |
| --- | --- | --- |
| Appropriation from chapter: | -- | -- |
| Value of donated items: | -- | -- |
| Other sources of income (list): | -- | -- |
| Total: | $0 | $0 |
| EXPENSES: |  |  |
| Value of donated items: |  |  |
| Other expenses (list): | -- | -- |
| Return of appropriation from chapter: | -- | -- |
| Total: |  |  |
| Return to chapter (profit) | $0 | $0 |

7.  List The Specific Steps To Bring This Project To A Successful Completion Showing Planned Dates For Each Step.

Update with dates and add to as needed.  This section ensures that the chairperson has a good idea of what needs to happen and when.

| Date | Action |
| --- | --- |
| 1/21 | Get CPG approved. |
| 1/22 | Submit information for website |
| 1/23-1/27 | Design flyer |
| 1/22, 1/29, 2/4 | Post information on list serv |
| 1/28 | Announce at meeting Allow members to sign up on interest sheet |
| 2/4 | Make reminder calls to people who signed up |
| 2/5 | Have a cheap bite to eat and a cocktail, and collect beads! |

IMPLEMENTATION AND EVALUATION

- Record any revision of the original plan.

- Calls were not made to people who signed up.  I just got too busy, and it didn’t get done.

- Information wasn’t necessarily posted on the listserve, because the listserve really doesn’t work anymore.  Instead, an event listing was set up on Facebook, and sent out to Jaycees.  It was also sent to the new listserve set up through Yahoo.

Materials/supplies not planned for:

Materials/Supplies	Resource/Contact Address/Phone	Actual Purchase/Donated Value

| Masks for parade participants | Chapter supplies | Approximately $10.00 |
| --- | --- | --- |

9.	What changes or recommendations do you have for a future chairman?  Try to make the time to call people who signed up on the preliminary sign up sheet.

10.	Give specific and measurable results for each goal established. Describe the impact of this project on the chapter, individual members and the community. Evaluate your primary purpose.

Restate your primary purpose and describe just how well the project met it. Then restate each of your goals and evaluate them here.  You can just copy, then paste your primary purpose, and goals from questions #2 here, then add a result line. Results can be evaluated by percentage. For example, if one goal was to have 25 people attend, and 50 actually attended, you can say you met that goal by 200%.

| Goal #1 | To have 5 Jaycee members attend. Met. We had 9 Jaycees attend, and 5 of those Jaycees were from the Arlington chapter. |
| --- | --- |
| Goal #2 | To have at least 3 potential Jaycees attend. Met. We had 4 potential Jaycees attend. |

INDIVIDUAL:  This project was rewarding to me because it gave me the opportunity to try out a bar that I had always wanted to try out.   It also was nice to attend something fun that I normally might have just done on my own, but was glad to share the experience with Jaycees that might not have been aware of this event otherwise.

CHAPTER:  I think this project was rewarding for the chapter as well.  It was nice to be able to interact and meet some of the Arlington Jaycees who came out for our event.  It also proved that we can go find fun outside of our Alexandria borders as long as it’s not a recruiting event.

COMMUNITY:  This project benefitted the Arlington community because they had spectators that were not necessarily Arlington citizens, and our food and beverage purchases helped expand the Arlington tax base.

Addendum:

| Project Chair(s) and Contact Info: | Name: Sharon S. |
| --- | --- |

| Cathy L. President, Alexandria Jaycees | Cathy oversees all projects conducted by the chapter. |
| --- | --- |
| Sharon S. Vice President, Membership Activation | Sharon oversees all projects in the Membership Activation portfolio. In addition, provides any additional support where needed. |